## Sheet1
Category	Group	Task	# Weeks
Training			8
Conference attendance			3
2.1 Software infrastructure		Build Bonsai ML API	8
		C#-Python communication	2
		C#-R communication	2
		C#-Matlab communication	2
		testing	4	18
2.2.1 Video-based behavioral analysis	MoSeq	learn functionality of MoSeq	2
		install and run MoSeq	1
		learn Moseq code	2
		use MoSeq to analyze data	2
		add online MoSeq state inferences to Bonsai behavioral video	2	9
	BehaveNet	learn functionality of BehaveNet	2
		learn BehaveNet code	2
		use BehaveNet to analyze data	2
		add online BehaveNet state inferences and reconstructed videos to Bonsai behavioral video	2	8
	PS-VAE	learn functionality	2
		learn code	2
		use to analyze data	2
		add online state inferences and reconstructed videos to Bonsai behavioral video	2	8
2.2.2.1 Spike sorting			8	8
2.2.2.2 Low-dimensional representations of spiking data	GLDS	learn LDS	2
		understand GLDS R code	2
		use GLDS to analyze neural data	2
		interface Bonsai with GLDS: compute latents for spikes recorded by Bonsai and display the latents in Bonsai	4	10
	PLDS	understand PLDS Matlab code	2
		use PLDS to analyze neural datad GLDS R code	2
		interface Bonsai with PLDS: compute latents for spikes recorded by Bonsai and display the latents in Bonsai	2	6
	HMM	learn about HMMs	2
		understand HMM R code	2
		use HMMs to analyze neural data	2
		interface Bonsai with PLDS: compute latents for spikes recorded by Bonsai and display the latents in Bonsai	2	8
	GPFA	learn about GPFA	2
		understand GPFA Matlab code	2
		use GPFA to analyze neural data	2
		interface Bonsai with GPFA: compute latents for spikes recorded by Bonsai and display the latents in Bonsai	2	8
	svGPFA	understand svGPFA Python code	2
		use svGPFA to analyze neural data	2
		interface Bonsai with svGPFA: compute latents for spikes recorded by Bonsai and display the latents in Bonsai	2	6
	LFADS	learn about autoencoders and RNNs	2
		understand LFADS Python code	2
		use LFADS to analyze neural data	2
		interface Bonsai with LFADS: compute latents for spikes recorded by Bonsai and display the latents in Bonsai	2	8
2.2.2.3 Low-dimensional representation of local-field potentials		extract LFPs from neuropixel recordings	2
		visualize LFPs in Bonsai	2
		apply GLDS, GPFA, HMM and LFADS to LFPs and visualize them in Bonsai	4	8
2.2.2.4 Neural decoding		add scikit-learn classifiers for independent features (support vector classifier, k-nearest neighbor, naive bayes, ANN)	3
		add sktime classifiers for time series	3	6
2.2.2.5 Comparing multiple data-analysis methods		neural data preprocessing	2
		neural data analysis with all methods	4	6
integration testing			8
documentation			12
workshop preparation			8
Total (weeks)			129
Total (years)			2.6875